## Project Decisions
PRD-to-User-Document Automation Agent — Project Design & Decisions
Prepared for: Head of Product ¦ Scope: Demo build ¦ Every feature, logic, architecture spec, and decision — with the reasoning behind each
1. FEATURES
Item | Reason / Rationale
Automatic PRD detection in Confluence | The whole point is to remove manual triggering. The agent watches a designated Confluence folder and starts work the moment a finalized PRD appears, so no one has to kick off the process by hand.
Title-based PRD recognition (final_PRD_<name>) | Gives a clear, unambiguous, agreed signal that a document is a finalized PRD ready for processing — avoids the agent acting on drafts, notes, or unrelated pages. Chosen as the demo convention for a reliable first gate.
LLM confirmation that a page is genuinely a PRD | Title alone can be wrong (mislabeled or empty pages). A second, content-based check by the model prevents the system from processing junk and wasting an entire downstream flow.
Rename-request task when a page is mislabeled | Instead of silently ignoring a wrongly-titled page, the agent asks the uploading PM to confirm and rename it. Keeps a human informed and turns an edge case into a gentle, actionable nudge rather than a dead end.
Locate-or-create the PRD-tracking ticket in Jira | Reflects reality: a tracking ticket may already exist (created by a person) or may not. The agent searches first and only creates one if needed, avoiding duplicates and respecting existing team workflow.
Automatic generation of the end-user document from the PRD | This is the core value: converting an engineer-facing PRD into a polished, public-facing user onboarding guide with zero manual drafting. Frees the PM to contribute judgment, not labor.
Self-critique pass in the authoring step | A cheap, one-round 'draft -> critique -> revise' loop measurably lifts output quality before a human ever sees it, reducing review rounds. Low cost, high return on document quality.
PM review loop via Jira comments | Keeps the human firmly in control of quality. Uses tools the PM already lives in (Jira), so no new interface to learn, and every round is tracked and auditable.
Structured feedback format (Section / Issue / Suggested change) | A predictable format lets the agent parse feedback reliably and apply changes precisely, reducing misinterpretation and rework.
Graceful handling of unstructured (plain-language) feedback | PMs are busy and won't always follow the format. Rather than failing, the agent restructures the feedback itself and asks the PM to confirm before acting — robust to real human behavior.
Confirmation-before-acting on restructured feedback | Prevents the agent from acting on a misreading. It shows the PM 'here's how I understood you — correct?' and waits, so no silent wrong edits ever reach the document.
Clarifying questions when the agent is genuinely blocked | Quality over speed: if an important point is unclear, the agent asks rather than guessing, improving the final document and mirroring how a good writer would behave.
Always tags the PM in replies (@mention) | Guarantees the PM is actually notified rather than relying on them to check the ticket — keeps the loop moving and avoids stalls caused by missed updates.
'Put yourself in the users' shoes' framing on every review request | Addresses a known real failure mode: PMs drifting into an engineer's point of view. A consistent nudge keeps the document centered on the end user, which is its entire purpose.
Explicit, self-service PASS signal (PM moves ticket to Done) | Removes all ambiguity about whether a draft is approved. Only the PM can pass it, and only by changing status themselves — so approval is deliberate, accountable, and never accidentally inferred by the agent.
Confirmation message to the PM on pass | Closes the loop politely and makes the state transition visible to the human, so the PM knows the system registered their approval.
Automatic creation of the User Document Publishing ticket | Moves the process forward without manual handoff, routing the passed document to the Head of Product for the final gate.
Head-of-Product final approval gate | Ensures nothing is published to production without senior sign-off — a deliberate control point protecting what becomes public-facing.
On approval: lock, move, and export the document | Locks the version (no further edits), moves it to the main folder, and exports a Markdown file for the future static-site generator — completing the lifecycle and feeding the downstream publishing step.
Markdown export to server storage for SSG | The end deliverable is a public doc site; storing clean Markdown now sets up the later SSG build without rework.
Error surfacing into Jira with a suggested fix + admin tag | When something breaks, a human is told immediately, in-context, with a proposed action — rather than a silent failure discovered days later.
Admin resume mechanism ('@agent resume') | Lets the admin fix an underlying issue and cleanly restart the failed step from its last checkpoint, without re-running the whole flow — fast, safe recovery.
LangSmith monitoring of latency, speed, and cost | Gives visibility into how fast and how expensive each run is, so the system can be tuned and its running cost stays transparent and controllable.
2. LOGICS
Item | Reason / Rationale
Decomposed 'Flow' of small triggered units, not one monolithic agent | Jira and Confluence already hold most of the authoritative state (ticket status, comments, versions). Small, independently-triggered, mostly-stateless units are simpler to build, test, and reason about than one large agent carrying everything.
Event-driven via webhooks | The system reacts to real events (page created, comment added, status changed) instead of constantly polling — lower latency, less wasted work, and a natural fit for the 'respond when something happens' nature of the workflow.
Explicit state machine with named stages | Each PRD moves through explicit stages (detected, drafted, awaiting_review, revising, passed, awaiting_publish_approval, publishing, complete). Explicit stages prevent the classic automation failure where 'what happens next' is guessed from data shape and silently goes wrong.
Checkpoint-and-resume rather than holding processes open | Waiting states (for PM feedback, for approvals) are recorded in the state store and the process exits; the next webhook resumes it. Nothing sits blocked in memory for hours or days, which is efficient and crash-safe.
Idempotency on every webhook | Jira and Confluence commonly deliver duplicate webhook events. Idempotency ensures a duplicate never double-processes (no duplicate tickets, no double edits) — essential for correctness.
Serial, one-PRD-at-a-time queue (demo) | Keeps behavior predictable and memory bounded on a small host, and removes concurrency bugs from the demo. Designed so parallelism can be added later without redesign.
Human-gated loops never auto-advance | The clarification and feedback-confirmation loops always wait for a real human reply. The agent never fabricates the PM's answer or proceeds on assumption at these gates — protecting document quality and trust.
Uncapped review loop until explicit pass | Quality is the priority; there's no arbitrary cutoff that would force through a not-yet-good document. The loop continues until the PM genuinely approves.
Feedback added after 'Done' is not processed | Makes the pass final and unambiguous. Prevents endless post-approval churn and keeps the state transition meaningful.
Brain / instinct / hands / memory separation | Agents (brains) decide; skill files (instincts) guide behavior; tools (hands) act on the world; the state store (memory) records progress. This separation means any piece can be changed without breaking the others — e.g. an API change only touches the tools.
Per-project routing before any work happens | Every incoming event is mapped to the correct project's configuration first, so the same code correctly handles multiple projects with different people, folders, and rules.
Retry-with-backoff before escalating errors | Transient API hiccups are common and self-resolving; automatic retries avoid bothering a human for blips, and only genuine failures escalate.
3. ARCHITECTURE
Item | Reason / Rationale
Multi-tenant single service (one deployment, routes by project) | One running service handles many projects by looking up per-project config, instead of duplicating the whole system per project. Far less to maintain and cheaper to run; a config change onboards a new project.
Config registry (projects.yaml) as the single source of project truth | All project-specific values (Jira projects, Confluence folders, PM, Head of Product, admin, export path) live in one plain-text file. This is the 'easy to mod' surface: swapping a reviewer or adding a project is a config edit, not a code change.
Strict config/code separation (no project literals in code) | Following the 12-factor principle. Keeping project keys, folder IDs, and account IDs out of the code makes the system portable, testable, and safe to reconfigure without engineering.
Role-specialized agents (Classifier, Ticket Manager, Author, Feedback Interpreter, Publisher, Error Handler) | Each agent has one clear job, its own context, and its own skill file. Specialization improves quality per task and makes each piece independently testable and tunable.
SKILL.md file per agent role | Behavior and quality standards live in readable, editable Markdown, not buried in code. This is the primary quality-tuning surface and can be adjusted without a developer.
Tools layer wrapping Jira / Confluence / filesystem | Generic, project-agnostic wrappers for external systems. If an external API changes, only this layer changes; the agents are insulated. Also keeps credentials and API detail in one place.
Repository-pattern state layer (SQLite now, Postgres-ready) | All state access goes through one module, so switching from SQLite (demo) to Postgres (scale) is a single-file change. Protects the 'easy to migrate' requirement without over-building now.
SQLite for the demo state store | Zero-setup, no separate database server, and entirely sufficient for single-tenant, one-at-a-time processing. The right-sized choice that avoids premature complexity and cost.
Self-built FastAPI wrapper as the entry point | A thin, well-understood web layer to receive webhooks and expose endpoints — full control, easy to test, and it keeps us on the free/open path (see licensing decision).
Packaged as a single Docker image | One reproducible artifact that runs identically anywhere, deploys cleanly to the VPS, and can be duplicated or migrated easily — supports the long-term manage/maintain/move requirement.
Persistent data volume (state DB + exported .md) | The state notebook and finished documents must survive restarts and rebuilds. Everything else can be torn down and rebuilt from code; only data and secrets are precious.
Secrets via environment (.env), never in code or config | Standard security hygiene — API keys and credentials are injected at runtime and never committed, keeping the codebase safe to share and store.
Anthropic Claude API as the single LLM provider | One provider keeps the demo simple, billing transparent, and behavior consistent across all agents. Chosen deliberately for the demo scope.
Public HTTPS endpoint with webhook signature validation | Atlassian must reach the service over the internet, so it needs valid TLS; validating webhook signatures prevents spoofed calls from triggering real Jira/Confluence writes — a security must, since the endpoint causes real actions.
4. DECISIONS & REASONING
Item | Reason / Rationale
Build a 'Flow' of small agents rather than one all-in-one agent | Chosen after weighing both: since Jira/Confluence already store the state, small triggered units give better quality and are easier to maintain — at the cost of owning an explicit state contract ourselves, which we accepted as the right trade.
Multi-tenant single service instead of duplicated per-project deployments | Duplicating a whole deployment per project scales resource use and maintenance linearly. A single service that routes by config is cheaper, easier to manage, and onboards new projects via a config edit.
Use LangChain/LangGraph's free MIT core behind our own wrapper (avoid the licensed server) | LangGraph's core orchestration library is MIT-licensed and free; only its packaged production server carries a license fee. Building our own FastAPI wrapper lets us use the framework's strengths at zero licensing cost on our own VPS.
Jira + Confluence as the entire human interface (no custom UI) | The people involved already work in these tools daily. Reusing them means no new interface to build or train anyone on, faster adoption, and every action is naturally logged and auditable.
PRD lives in Confluence; final User Document exported as Markdown | Confluence suits collaborative review; Markdown is the clean, portable input the future static-site generator needs. Each format is used where it fits best.
Pass signal = PM changes ticket status to Done, themselves, only | The most unambiguous, accountable approval signal available. Making it self-service and status-based removes any risk of the agent inferring approval incorrectly, and makes clear that post-Done feedback is not actionable.
Single Head-of-Product approver for publishing | Keeps the final gate simple and clear for the demo, avoiding the added complexity of multi-approver tracking while still enforcing senior sign-off before anything goes public.
Detection via Confluence webhook (push), not polling | Lower latency and less wasted work than repeatedly polling a folder — the agent reacts the moment a PRD lands.
Title convention final_PRD_<name> as the demo recognition rule | A simple, reliable, agreed signal for the demo. It gives a dependable first gate and can be made more sophisticated later if needed.
No fixed document template — the agent tailors structure per PRD | A good user guide for a small feature and for a whole product look different. Letting the agent (guided by its skill file and prompt) choose the best structure produces higher-quality, fit-for-purpose docs. Structure lives in the prompt/skill, so it's tunable.
Include a self-critique loop; defer RAG and heavy orchestration | The self-critique loop is cheap and improves quality now. RAG (for house-style consistency across many docs) and heavier frameworks add complexity with no payoff at demo scale, so they're deliberately deferred with clean seams left open.
Errors escalate to a per-project admin with a resume keyword | Keeps a human in the loop for genuine failures, in-context in Jira, with a fast, safe recovery path — rather than silent failure or a full restart.
Reviewers/assignees (PM, Head of Product, admin) fixed in config | These change occasionally and must be swappable without code. Putting them in the config registry directly satisfies the 'easy to replace reviewers' requirement.
Process multiple simultaneous PRDs one at a time (queue) for the demo | Predictable behavior, bounded memory on a small host, and no concurrency bugs to debug during the demo — with the design left open to add parallelism later.
Deploy on DigitalOcean Droplet, Basic/Regular SSD, 1 GB, Ubuntu LTS | Cheapest appropriate host for a single-tenant demo. Ubuntu LTS is the best-documented, long-supported OS for this Python/Docker stack. The 1 GB size is a deliberate cost choice, with documented mitigations and an easy resize path if it proves tight.
Build the Docker image off the Droplet and pull it down | A Docker build on a 1 GB box can run out of memory and fail. Building elsewhere and pulling the finished image is the standard, reliable way to keep the tight host stable — a known condition, planned for rather than discovered.
SQLite now, with a repository layer so Postgres is a one-file swap later | Right-sizes the demo (no DB server, no cost) while protecting the future path to multi-tenant scale — deliberately avoiding both over-building now and a painful rewrite later.
Demo-first, tune-later philosophy throughout | Get a genuinely working end-to-end demo first; refine quality behaviors via prompts and skill files afterward. Focuses effort on proving the concept before polishing, and keeps the tunable parts in plain text.